## Slide 1
ELITE WORLD SERVICES · AVIATION RECRUITMENT
DRIVE-DAY PLAYBOOK · EDITION 2026.05
The drive runs itself. Your job is to keep it calm.
Step-by-step guide for desk operators, recruiters and floor team. Covers the entire student journey — arrival to result — and every issue we've seen in testing.
FOR: ON-SITE EWS TEAM (DESK OPERATORS · RECRUITERS · FLOOR)
careers.ews.aero · Live system snapshot · Updated 2026-05-28

## Slide 2
INSIDE THIS PLAYBOOK
Eight parts. Read in order on day-1.
01
Before the doors open
T-60 min · venue & system pre-flight
02
How a student moves through the venue
End-to-end flow on one page
03
Roles at the desk
Who does what · how to swap places
04
Calling tokens & running interviews
The recruiter loop
05
Crowd control & no-shows
The desk operator playbook
06
Live monitoring
The super admin's dashboard during the drive
07
When things go wrong
Symptom → cause → fix
08
Wrap-up & exports
Selection list, CSV, photo backup

## Slide 3
PART 01
Before the doors open
T-60 minutes. 8 checks. If all green, you're ready.
UU Aviation Recruitment 2026 · Drive-Day Playbook
3 / 21

## Slide 4
PART 01 · PRE-FLIGHT
8-step venue + system check
1
1. Power up the TV / display monitor
Open Chrome → https://careers.ews.aero/display → press F11 for full-screen. Token board should show the room cards. Auto-refreshes every 5 sec.
2
2. Hang the QR poster at the entrance
Print from /admin/qr-poster (super admin only). One QR per entrance is enough. Students scan → land directly on /register.
3
3. Recruiters log in at their laptops
https://careers.ews.aero/admin/login → email + password (no OTP). Each recruiter sees their assigned room auto-selected.
4
4. Desk operator logs in
Same URL, same flow. Desk operator's home screen is the live queue at /admin/queue.
5
5. Open the runbook for quick reference
/admin/runbook → print 1 copy and keep at the desk. Same content as this deck, compressed to a single A4 sheet.
6
6. Sanity-check the live tiles
Open /admin in another tab. Registered/Waiting/Done numbers should match reality. If they don't refresh — check Vercel status (super admin).
7
7. Brief the floor team (volunteers)
Two volunteer roles: 'Greeter' (helps students scan QR), 'Caller' (walks the waiting area calling token numbers from the TV).
8
8. Open this playbook bookmark on every device
https://careers.ews.aero/admin/runbook — the runbook page mirrors this deck.
If any of these 8 steps fail → call the super admin BEFORE opening doors. Do not improvise.
UU Aviation Recruitment 2026 · Drive-Day Playbook
4 / 21

## Slide 5
PART 02
How a student moves through the venue
Six stops. Roughly 8–12 minutes per student end-to-end.
UU Aviation Recruitment 2026 · Drive-Day Playbook
5 / 21

## Slide 6
PART 02 · THE STUDENT JOURNEY
From entrance to result — one screen at a time
1
Stop 1 · Entrance
Greeter points to the QR poster. Student scans → phone opens https://careers.ews.aero/register.
2
Stop 2 · Registration form (5 min)
Student enters details + uploads resume + photo (compressed automatically in-browser so phone-camera photos don't fail). Submit → token issued.
3
Stop 3 · Token & admit card
Success screen shows BIG green token number. Student downloads the PDF admit card (also emailed). They keep this on their phone.
4
Stop 4 · Waiting area
Student watches the TV. Display shows which room is calling which token. Updates every 5 sec.
5
Stop 5 · Interview
When their number shows up next to a room, they walk to that room. Recruiter has their full profile + resume + photo on screen.
6
Stop 6 · Result
Recruiter saves decision → student gets an automatic email with the outcome. They can leave the venue.
No paper forms. No phone calls. No SMS. Everything is on the TV or in email.
UU Aviation Recruitment 2026 · Drive-Day Playbook
6 / 21

## Slide 7
PART 03
Roles at the desk
Four roles. Each one has a screen. None of them step on each other.
UU Aviation Recruitment 2026 · Drive-Day Playbook
7 / 21

## Slide 8
PART 03 · ROLES — TIER 1
Recruiter & Desk Operator (the busy ones)
RECRUITER
■ Logs in at /admin/login. Sees ONLY their room.
■ Clicks 'Call Next Token' to summon the next student.
■ Reviews the student profile on screen, conducts interview.
■ Records: rating 1–5, notes, decision (shortlist / hold / etc.).
■ Toggles 'Auto-advance' → call the next one immediately after save.
■ Cannot see or modify other rooms.
DESK OPERATOR
■ Logs in at /admin/login. Lands at the LIVE QUEUE.
■ Watches the full waiting list across all rooms.
■ Helps no-shows: re-issues skipped tokens via 'Recall'.
■ Marks permanent no-shows so they stop appearing in the queue.
■ Cannot record interview decisions — only manages flow.
■ First point of contact for confused or upset students.
FLOOR (no login)
■ Greeter at entrance: helps students scan QR, hands out a backup paper QR if their phone is dead.
■ Caller in waiting area: reads token numbers off the TV every 30 sec for students who missed it.
■ Runner: physically walks no-shows from the waiting area to the recruiter room.
UU Aviation Recruitment 2026 · Drive-Day Playbook
8 / 21

## Slide 9
PART 03 · ROLES — TIER 2
Email Manager & Super Admin (the office roles)
EMAIL MANAGER
■ Sends post-drive announcements to filtered groups (e.g. all SELECTED, or all REJECTED).
■ Uses /admin/emails: pick audience → preview count → type confirmation if > 25 → send.
■ Does not touch the queue, rooms, or interviews.
■ Can export the full student list as CSV from /admin/students.
SUPER ADMIN (founder)
■ Creates all staff accounts at /admin/users.
■ Assigns each RECRUITER to a room from the same page (dropdown).
■ Watches live analytics + tile counts at /admin.
■ Has access to ALL other panels for support / firefighting.
■ Only role that can use the emergency env-var password.
ROLE SWAPS
■ All staff log in with the SAME URL — only the role differs.
■ If a recruiter calls in sick: super admin reassigns their room to a stand-by recruiter from /admin/users.
■ Desk operator backup: any super admin can use /admin/queue.
■ Never share a login. Make a new account in 30 seconds.
UU Aviation Recruitment 2026 · Drive-Day Playbook
9 / 21

## Slide 10
PART 04
Calling tokens & running interviews
The recruiter screen — what every click does.
UU Aviation Recruitment 2026 · Drive-Day Playbook
10 / 21

## Slide 11
PART 04 · THE RECRUITER LOOP
6 clicks per student
1
1. Click 'Call Next Token'
Pulls the lowest WAITING token into your room. The student sees their token appear next to your room name on the TV.
2
2. Wait ~30 sec for the student to walk in
If they don't show up: click 'Skip (no-show)'. Token goes to SKIPPED. Desk operator can recall later.
3
3. Click 'Start interview'
Marks the token IN_PROGRESS. Begins timing the interview (used in analytics).
4
4. Conduct the interview
Student profile, resume preview, and photo are right there. Take notes in the box — they're saved with the decision.
5
5. Pick a decision + rating
5 options: Shortlist · Hold · Re-interview · Reject · SELECTED. Rating is 1-5 stars. Notes are optional but encouraged.
6
6. Click 'Save & Next'
Decision is locked. Student gets an automatic email with their result. If 'Auto-advance' is on, your screen instantly calls the next token.
Average interview: 8 min. With auto-advance on, you handle ~7 students/hour.
UU Aviation Recruitment 2026 · Drive-Day Playbook
11 / 21

## Slide 12
PART 05
Crowd control & no-shows
The desk operator's playbook — keep the line moving.
UU Aviation Recruitment 2026 · Drive-Day Playbook
12 / 21

## Slide 13
PART 05 · DESK OPERATOR
Live-queue mastery
WHEN TO INTERVENE
■ Token waiting > 20 min → check if the student is still in the venue
■ A room is idle but the queue is long → call that recruiter on the phone
■ Same name registered twice → keep the latest token, no-show the older one
■ Student says they didn't get the email → resend from /admin/students/[regId]
■ Student says 'I can't find my token number' → search by name in /admin/students
THE 4 BUTTONS YOU USE
■ Recall — Brings a SKIPPED token back to the front of WAITING. One click.
■ No-show — Permanent — token disappears from the queue. Use only after 2 callbacks.
■ Filter chip 'Skipped' — Shows just the skipped tokens. Easiest to recall in batch.
■ Search by token # — Top of the queue page. Type the number → jump to row.
Rule: never delete a token. Use 'No-show'. Deletion would break analytics + the student's email trail.
UU Aviation Recruitment 2026 · Drive-Day Playbook
13 / 21

## Slide 14
PART 06
Live monitoring
The super admin's dashboard — what to watch, what to ignore.
UU Aviation Recruitment 2026 · Drive-Day Playbook
14 / 21

## Slide 15
PART 06 · WATCH THESE NUMBERS
Real-time dashboard at /admin
GREEN — KEEP DOING IT
■ Registered count climbing steadily (~2/min during arrival rush)
■ Waiting < In-progress × 4 → flow is balanced
■ All 4 room cards on /display showing a 'Now serving' badge
■ Completed count rising at ~1 every 90 sec (across all rooms)
■ No 'Failed' emails in the audit log
AMBER / RED — INVESTIGATE
■ AMBER — Waiting > 50 students → ask if a recruiter is stuck
■ AMBER — One room hasn't called a token in 15 min → recruiter break or laptop issue
■ RED — Tiles stopped updating → page is stale, refresh the browser
■ RED — Registered count went BACKWARDS → call the dev immediately (data integrity issue)
■ RED — Display TV shows '—' for all rooms → DB or Vercel outage, check status pages
The /admin overview page now loads in ~350 ms warm. If it spins for > 5 sec → something is wrong (not just slow).
UU Aviation Recruitment 2026 · Drive-Day Playbook
15 / 21

## Slide 16
PART 07
When things go wrong
Twelve scenarios we've seen in testing. Fix flow under each.
UU Aviation Recruitment 2026 · Drive-Day Playbook
16 / 21

## Slide 17
PART 07 · TROUBLESHOOTING — STUDENT SIDE
Most common issues at the entrance and registration
SYMPTOM
CAUSE
DO THIS
QR code won't scan
Phone camera dirty or QR too small from distance
Hand them the paper QR card (printed copies kept at desk) — same URL
Form rejects their phone photo
File over 2 MB after compression
Tell them to retake with lower resolution OR upload from gallery. Compression is automatic.
'Email already registered' error
They tried earlier — their token already exists
Search by email in /admin/students → give them the existing token number
OTP email never arrives
OTP is OFF in current config — should never see this
If they do see it: super admin pushes APP_STUDENT_AUTH=none again on Vercel
Admit card PDF won't open on their phone
Older Android browsers don't render Vercel-served PDFs inline
They can still attend with just the token number. Email also has the number.
Submit form spins forever
Their phone signal dropped mid-upload
Re-submit when signal returns. Server checks for duplicate email — won't double-register.
Rate-limit: a single phone is capped at 5 submissions / 10 min. Don't worry — this is to block bots, not a real student issue.
UU Aviation Recruitment 2026 · Drive-Day Playbook
17 / 21

## Slide 18
PART 07 · TROUBLESHOOTING — STAFF SIDE
Issues recruiters and desk operators may hit
SYMPTOM
CAUSE
DO THIS
Recruiter sees 'No room assigned to you yet'
Their account exists but Room.recruiterId isn't set
Super admin opens /admin/users → finds their row → picks a room from the dropdown → done. Recruiter refreshes.
Login says 'Too many attempts'
10 failed logins from this IP in 5 min — 15-min cooldown kicked in
Wait it out. Or: super admin uses a different device/network OR the emergency password.
Decision form rejects 'Token is not in this room'
Their room reassignment happened mid-interview, OR a stale tab
Refresh the recruiter page. The new room context loads correctly.
Display board frozen for everyone
TV browser tab crashed or lost network
Refresh the TV browser (Cmd/Ctrl+R). It auto-resumes.
Bulk-email send won't trigger
Audience > 25 — typed confirmation required (anti-mistake guard)
Type the EXACT number shown in the recipient count, then click Send.
CSV export downloads empty file
Filter selected zero students — there's nothing to export
Clear all filters → re-export. Headers always present even if zero rows.
Every recoverable error tells you what to do in the error message itself. Read it before calling for help.
UU Aviation Recruitment 2026 · Drive-Day Playbook
18 / 21

## Slide 19
PART 08
Wrap-up & exports
After the last student walks out — what to deliver.
UU Aviation Recruitment 2026 · Drive-Day Playbook
19 / 21

## Slide 20
PART 08 · END-OF-DAY
5 things to do before you go home
1
1. Confirm zero WAITING tokens
Open /admin/queue → filter 'Waiting'. Should be empty. If not: are they actually here? No-show or recall.
2
2. Run the selection email blast
Email Manager opens /admin/emails → audience: SELECTED → write congrats email → type recipient count to confirm → Send.
3
3. Export the full student CSV
/admin/students → 'Export CSV' top right. Includes ALL students, all statuses. Keep this file safe — it's your audit trail.
4
4. Take a screenshot of /admin tiles
The final numbers for the day. Goes in the post-drive report.
5
5. Hand over to the super admin
They run the post-drive backup script + archive the Supabase data.
UU Aviation Recruitment 2026 · Drive-Day Playbook
20 / 21

## Slide 21
You've got this.
The system handles 700 students. Your job is to keep humans calm.
When in doubt: read the runbook printout at the desk. When the runbook doesn't help: call the super admin. When the super admin doesn't pick up: the system keeps running even if you click nothing — students keep registering, tokens keep flowing.
QUICK CONTACTS
Super admin: bhupender@eliteworldservices.com · Live URL: careers.ews.aero · Runbook: careers.ews.aero/admin/runbook
UU Aviation Recruitment 2026 · Drive-Day Playbook
21 / 21